Capstone Proposal Template

Capstone Project Proposal

1. Project Title

## Predictive Modeling of Population Decline, Economic Resilience, and Demographic Momentum in Puerto Rico

2. Team Members & Roles

- Jose Andres Riveraruiz

- Role: Responsible for end-to-end execution, including data harmonization across multiple sources, supervised and unsupervised model development, and translating analytical outputs for policy stakeholders.

3. Problem Statement

- Problem: Puerto Rico is trapped in reinforcing feedback loops of population decline, low fertility, and economic/environmental shocks. Existing tools are primarily descriptive and fail to distinguish between structural demographic "momentum" and migration-driven loss.

- Stakeholders: The Puerto Rico Planning Board (Junta de Planificación), policymakers, and resilience researchers.

- Insight/Decision Support: This project will support evidence-based resource allocation by quantifying risk and identifying which municipalities are shrinking due to underlying demographic fundamentals versus external shocks.

4. Motivation & Impact

- Importance: Sustained sub-replacement fertility means many areas will continue to shrink even without migration. Understanding this is critical for long-term planning in workforce development and service provision.

- Success Impact: Success will enable earlier identification of high-risk municipalities and provide an actionable "Demographic Vulnerability Score" to prioritize infrastructure and resilience investments.

5. Data Description

- Data Sources:

  - Demographics: U.S. Census PEP (2010–2024) and PR Vital Statistics.

  - Economic: ACS Labor Market indicators and County Business Patterns (payroll/establishments).

  - Hazards: NOAA hurricane tracks and USGS earthquake catalogs.

- Size and Structure: A harmonized municipal-level panel dataset stored in standardized JSON/CSV formats. CSV, JSON and Python files are in the MB size.

- Limitations: Small-area component data (especially migration) can be noisy or sparse, requiring careful validation.

- Access and privacy considerations: All data are publicly available and contain no personally identifiable information.

6. Proposed Methodology

- Initial Modeling Approach:

  - Supervised: Regularized regression (Ridge, Lasso) and tree-based methods (Random Forest, Gradient Boosting) to forecast population change.

  - Unsupervised: K-means or hierarchical clustering to create a municipal typology.

- Baselines:

  - Linear Trend: A baseline using ordinary least squares (OLS) regression based solely on historical population totals to project future counts, ignoring economic and hazard covariates.

  - Standard Cohort-Component Projection: Utilizing traditional demographic projections (projecting births, deaths, and migration separately) to compare against the supervised learning approach.

  - Mean/Median Change Baseline: A simple model that predicts the average or median percent population change across all 78 municipalities as the forecast for every individual municipality.

- Planned Feature Engineering: Engineering proxies for demographic momentum, including crude birth rates, age structure (e.g., % under 15), and employment change trends.

- Tools and Libraries: Python-based stack for data engineering, Scikit-Learn for modeling, and SHAP/Permutation Importance for interpretability.

7. Evaluation Plan

- Success Metrics: Mean Absolute Error (MAE) and Root Mean Squared Error (RMSE) for forecasts.

- Validation Strategy: Utilize temporal cross-validation and out-of-sample testing to ensure model stability over time. This includes a specific focus on Hurricane Maria (2017) as a validation window to test the model’s ability to distinguish between shock-driven decline (the post-2017 migration surge) and the underlying demographic momentum established during the 2010–2016 period.

- Risks: Data availability for specific years; mitigation includes using fertility proxies and sensitivity analysis.

8. Expected Deliverables

- Final report: A written capstone report documenting data, methods, results, and policy implications.

- Presentation: A formal capstone presentation summarizing findings and insights.

- Code repository: A documented, reproducible codebase stored on Github: https://github.com/Venettov/CAPSTONE_DATA_SCIENCE_RIVERARUIZ.git

- Optional dashboard or demo: Documented Dashboard is already started at https://venettov.github.io/CAPSTONE_DATA_SCIENCE_RIVERARUIZ/

9. Timeline & Milestones

- Week-by-week plan:

| Phase | Timeline | Key Activities | Milestones & Deliverables |
| --- | --- | --- | --- |
| I: Data Engineering | Weeks 1–3 | Data acquisition and harmonization of Census, Vital Statistics, and hazard data into a municipal-level panel. Initial engineering of demographic momentum and economic proxies. | Milestone: Finalized, standardized wide-format JSON/CSV dataset ready for modeling. |
| II: Supervised Modeling | Weeks 4–6 | Development and tuning of Ridge/Lasso and tree-based forecasting models. Validation testing focused on the Hurricane Maria (2017) window to distinguish shock-driven decline from structural momentum. | Milestone: Validated population change forecasts with documented metrics. |
| III: Advanced Analytics | Weeks 7–9 | Application of K-means/hierarchical clustering to establish municipal typologies. Model explainability analysis using SHAP values to identify key drivers of decline. | Milestone: Composite Municipal Demographic Vulnerability Scores and driver rankings. |
| IV: Synthesis & Reporting | Weeks 10–12 | Scenario simulation and development of spatial visualizations for the dashboard. Drafting of the final capstone report and presentation materials. | Milestone: Final submission of report, code repository, and live dashboard demo. |

- Internal checkpoints:
A milestone review will be conducted at the conclusion of each phase to validate model performance and ensure alignment with stakeholder objectives

10. Risks, Challenges, and Mitigation

- Data Noise: Migration data is often volatile.

- Scope risks: Overexpansion of modeling complexity.

- Technical uncertainties: Balancing "black box" model performance with policy interpretability.

- Mitigations: Emphasis on demographic momentum variables, interpretable models, and clear scope boundaries. Using robust tree-based models and explainability tools to ensure results are transparent for non-technical stakeholders.